## PB
Product Backlog
Remaining effort after sprint
User Story | Details | Prio | Value | Init effort | 1 | 2 | 3 | 4 | 5 | 6
Studenten kunnen toetsen maken |  | 1 | 7 | 5
Administrator accounts kunnen lessen en toetsen uploaden/bewerken |  | 2 | 6 | 3
Gebruikers kunnen inloggen |  | 3 | 6 | 5
Als een gebruiker inlogt wordt er gezien of het een student/administrator account is |  | 4 | 4 | 2
Gebruikers kunnen scores bekijken |  | 5 | 4 | 2
Administrator accounts kunnen scores van studenten bekijken |  | 6 | 5 | 5

## SP1
Sprint 1 Backlog
Remaining effort after day
User Story | Sprint Task | Teamlid | Init effort | 1 | 2 | 3 | 4 | 5 | 6
As a buyer I want to place a book in a shopping cart | Modify database | Joan | 5 | Remaining effort after day 1: 3; Remaining effort after day 2: 2; Remaining effort after day 3: 0
| Create webpage UI | Jeroen | 11 | Remaining effort after day 1: 7; Remaining effort after day 2: 5; Remaining effort after day 3: 5
| Create webpage (Javascript logic) | Lambert | 12 | Remaining effort after day 1: 12; Remaining effort after day 2: 8; Remaining effort after day 3: 6
| Automated acceptance tests | Erik | 9 | Remaining effort after day 1: 4; Remaining effort after day 2: 2; Remaining effort after day 3: 2
| Update buyer help webpage | Lambert | 1 | bar: Remaining effort after day 1 to Remaining effort after day 3
As a buyer I want to remove a book from a shopping cart | Merge PHP code | Jeroen | 2 | Remaining effort after day 1: 2; Remaining effort after day 2: 0; Remaining effort after day 3: 0
| Complete layer level test | Lambert | 5 | Remaining effort after day 1: 4; Remaining effort after day 2: 3; Remaining effort after day 3: 2
| Change reader http API | Erik | 8 | Remaining effort after day 1: 8; Remaining effort after day 2: 8; Remaining effort after day 3: 6